Permitting Road Map
National Park Service (NPS) - Denver Service Center (DSC) | 8-11-26
Project Information
	Date:	mm/dd/yyyy	Park Code:	example: NAMA	Project Management Information System (PMIS) Number:	XXXXXXX		
	To:	Names of DSC Project Manager and DSC Contracting Officer	From:	Project Manager, Firm Lead and/or Permit Lead, Firm Name 
	Project Name:	(Official Name in PMIS) 
Instructions
The Permitting Road Map outlines the requirements of each permit identified in the Permitting Assessment Form (PAF) and transitions the DSC Project Permitting Process (PPMP) from Scoping to begin Planning.
Architect/Engineer (AE) Requirements
· Outline each permit's requirements throughout design, construction, closeout, and operational phases.
· Recommend which permits should be acquired during design or construction.
· Recommend if a full Permit Plan is required. Discussed during end of Schematic Design (SD) permitting meeting. Typically, permits acquired during design require a Permit Plan.

	Permit
(Exact name
of permit)
	Agency Issuing Permit
(Name of Agency
& Branch)
	Jurisdiction
(Federal / States / Local Name)
	Notes
(Number(s) from Notes section below)
	Acquisition
(Design or Construction or Operation)
	Permit Plan Required
(Yes / No))
	Design Phase Requirements
	Construction Phase
Requirements
	Closeout Requirements
	Operational Requirements

	
	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	
	

	Add Rows as Needed
	
	
	
	
	
	
	
	
	

	Example Permits Below
	
	
	
	
	
	
	
	
	

	Example: CWA (Clean Water Act) §404 -Nation Wide Permit (NWP), #3 (Maintenance)
	USACE (US Army Corps of Engineers), Sacramento District

	Federal
	1-2
	Design 
	Yes
	Predesign meeting, permit documentation development, application assembly (including a Compensatory Mitigation Plan), application submittal, 90-day USACE review, permit issued, permit review acceptance & signed, final integration into Request for Proposal (RFP).
	Implementation of permit provisions (project start and conclusion notification)
	NWP has general requirements that include closure, transfer of Compensatory Mitigation Plan to Park
	Park executes Compensatory Mitigation Plan

	Example: CWA §402 - NPDES (National Pollutant Discharge Elimination System) Construction General Permit (aka SWPPP (Stormwater Pollution Prevention Plan))
	CA RWQCB (California Regional Water Quality Control Boards), Fresno Office

	Federal, administered by state
	3
	Construction
	No
	Review current standards, develop required sheets, included in Division 1 Specifications (015723), note not needed for closure in Division 1 Specifications (017700-1.5).
	Prepare SWPPP, File NOI, conduct during construction monitoring, and follow provisions
	File Notice of Termination (NoT)
	None



Notes:
1. Example: NWP 3 – First 30-days of review period is for determination of application completeness. If the application is found incomplete, then the 30-day period can be paused or reset. 
2. Example: NWP 3 – The Mitigation Plan is required due the area (0.2 acres) of the impacts. The preparation of the Mitigation Plan should be a separate task / sub-task and will need to involve Compliance. 
3. Example: SWPPP – Because of the way California administrators the SWPPP, it will be important to identify the LEVEL during design and include the requirements into the SOS (Scope of Services) / sheets / specifications. 
4. 
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